## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US001 | As a user, I should be able to upload sales call audio for analysis | MUST HAVE | Streamlit setup | Aliya Khanum | 3- Completed
2 | 2 | US001 | As a system, I should transcribe audio to text accurately | MUST HAVE | Google Speech API | Aliya Khanum | 3- Completed
3 | 3 | US001 | As a system, I should detect customer sentiment from text | MUST HAVE | TextBlob NLP | Aliya Khanum | 3- Completed
4 | 4 | US001 | As a user, I want the system to identify speakers separately | SHOULD HAVE | pydub silence split | Aliya Khanum | 3- Completed
5 | 5 | US001 | As a system, I should suggest sales responses automatically | SHOULD HAVE | Sentiment output | Aliya Khanum | 3- Completed
6 | 6 | US001 | As a user, I want to record audio so that I can generate transcripts | MUST HAVE | Recorder module | Aliya Khanum | 3- Completed
7 | 7 | US001 | As a user, I need to convert WebM to WAV | MUST HAVE | FFmpeg | Aliya Khanum | 3- Completed
8 | 8 | US001 | As a user, I want to upload audio files | SHOULD HAVE | File uploader | Aliya Khanum | 3- Completed
9 | 9 | US001 | As a user, I want real-time or near-real-time transcription | SHOULD HAVE | Whisper/Google API | Aliya Khanum | 3- Completed
10 | 10 | US001 | As a user, I want sentiment analysis for each transcript | SHOULD HAVE | TextBlob | Aliya Khanum | 3- Completed
11 | 11 | US001 | As a user, I want audio recorded through browser mic, so that I can analyze call in real-time | MUST HAVE | FFmpeg Setup | Aliya Khanum | 3- Completed
12 | 12 | US001 | As a user, I want customer-only NLP sentiment, intent, and entity extraction | MUST HAVE | Google STT | Aliya Khanum | 3- Completed
13 | 13 | US001 | As a user, I want convert uploaded audio formats reliably | MUST HAVE | FFmpeg | Aliya Khanum | 3- Completed
14 | 14 | US001 | As a system, I should maintain call history list | COULD HAVE | Session state | Aliya Khanum | 3- Completed
15 | 15 | US001 | As a user, view sales suggestions | SHOULD HAVE | LLM | Aliya Khanum | 3- Completed
16 | 16 | US001 | As a user, enable LLM-based reasoning | COULD HAVE | LLM | Aliya Khanum | 3- Completed
17 | 17 | US001 | As a system, fallback to offline reasoning | MUST HAVE | LLM | Aliya Khanum | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7